## Sheet1
Action Register
Last Updated: | 13th August 2026
Projhect | Action # | Action Title | Detail | Owner | Company | Date Allocated | Due | Actual Completion date | Status | Status Comments
RACV_Noosa BESS | 1 | Noosa – PV (DNSP) | Energex confirmed; site energising this week (main reception + enclaves live). [Raised 21/07] | Brent Craig (BC) | RACV | 2026-06-01 | 2026-08-20 |  | Open | Works still underway
RACV_Cobram BESS | 1 | Cobram – BESS (fence) | Fence colours confirmed — bushland enclosure / woodland-grey roller door. [Raised 21/07] | Brent Craig (BC) | RACV | 2026-06-01 | 2026-08-20 | 2026-08-20 | Closed | Works still underway
RACV_Goldfields Solar | 1 | Noble Park – EV (Stage 1) | Line marking completed; bays open for charging from tomorrow. [Raised 28/07] | David Luca (DL) | Major Works | 2026-06-01 | 2026-08-20 |  | Open | Works still underway
RACV_Goldfields Solar | 2 | Baseline programme | Updated baseline build schedules issued to Brent. [Raised 28/07] | David Coulthard (DC) | CES | 2026-06-01 | 2026-08-20 |  | Open | Works still underway
RACV_Goldfields Solar | 3 | Cobram – BESS (tree limb) | Assess the tree limb overhanging the battery — Brent to raise with Andy; David to send Roger's notes / photos. [New 05/08] | Brent Craig (BC) | RACV | 2026-06-01 | 2026-08-20 |  | Open | Works still underway
RACV_Goldfields Solar | 4 | Noble Park – PV (backstop) | Track down and confirm the backstop-testing method (Andrew Nimmo, United Energy); check with Vincent first, then energise half. [Raised 28/07] | David Coulthard (DC) | CES | 2026-06-01 | 2026-08-20 |  | Open | Works still underway
BEXT_Project Start Up | 1 | Healesville (RFIs / data) | Brent to close the remaining RFIs via Grosvenor (approx. $4.5k PO across several sites); David to forward the RFI list & PO. [Raised 28/07] | Brent Craig (BC) | RACV | 2026-06-01 | 2026-07-15 | 2026-07-20 | Closed | Works still underway
BEXT_Project Start Up | 2 | Royal Pines – S1 (pricing) | Issue the three-contractor cost breakdown to Adam & Jonathon for approval; SJ tightening its price. [Raised 21/07] | David Coulthard (DC) | CES | 2026-06-01 | 2026-08-20 |  | Open | Works still underway
BEXT_Project Start Up | 3 | Royal Pines – DHW | Get an indicative design cost (Stable) so the load is captured in the max-demand. [Raised 21/07] | David Coulthard (DC) | CES | 2026-06-01 | 2026-08-20 |  | Open | Works still underway
BEXT_Project Start Up | 4 | Cobram – heat pump (RFI register) | Create the RFI register for the hot-water / heat-pump replacement and share with Brent. [New 05/08] | David Coulthard (DC) | CES | 2026-06-01 | 2026-08-20 |  | Open | Works still underway
BEXT_Project Start Up | 5 | Contracts (admin) | David to send Brent dot-point contractor headlines + fee proposals; Brent to draft contracts. [New 05/08] | David Luca (DL) | Major Works | 2026-06-01 | 2026-08-20 |  | Open | Works still underway