| HTHA & RACV — RACV Property Electrification |  |
| --- | --- |
| Weekly Program Check-in — Meeting Minutes |  |
| Program | RACV Property Electrification — Weekly Program Check-in |
| Date | Wednesday, 5 August 2026 |
| Time | 10:00 – 10:45am |
| Venue | Microsoft Teams |
| Meeting # | [ ] |
| Minutes by | David Coulthard |

| Attendees |  |  |  |
| --- | --- | --- | --- |
| Attendee | Initials | Company | Email |
| David Coulthard | DC | CES | David.Coulthard@htha.com.au |
| Ched Bresland | CB | CES | Chedryian.Bresland@racvsolar.com.au |
| Brent Craig | BC | RACV | Brent_Craig@racv.com.au |
| Mark Farage | MF | RACV | Mark_Farage@racv.com.au |
| Shane Leslie | SL | RACV | shane_leslie@racv.com.au |
| Jonathon Vains (apology) | JV | RACV | jonathon_vains@racv.com.au |

| - Safety |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | Detail | Owner | Due | Status |
| Toolboxes & comms | Regular toolboxes and contractor communication — no complacency on safety, quality and housekeeping. | David / Ched | Ongoing | Open |
| Safety standards | Ched-led safety meetings continuing; focus on lifting safety standards and expectations across all contractors. | Ched | Ongoing | Open |
| Site records & IT security | Standardising all site photos and progress records onto Procore (aligned with the IT security policy); contractors being onboarded across every site. | David / Ched | Ongoing | Open |

| - Project Status |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Status key: On Track · Monitor · At Risk · On Hold · Complete |  |  |  |  |  |  |
| Project | Phase | Status | This Week’s Update | Next Action | Owner | Due |
| Noosa – PV | Delivery | On Track | Energising underway — main reception and several enclaves now live and facing the grid. Contractor (Stony) on site with the resort commissioning room by room and adding them to the portal; ~3 rooms left. All Precincts, Enclaves and main reception expected energised by end of this week. Major milestone. Network / DNSP: Energex — approved and confirmed. | Complete remaining rooms and close out by end of week. | David | End of week |
| Noosa – LV Upgrade | Design | On Track | With Adam Lane and David; a further design / maximum-demand review with Matt Douglas is booked this week. Matt has issued POs — Adam to confirm coverage and allocation. RACV to coordinate the revised Energex connection offer. Network / DNSP: Energex — RACV to manage the revised connection offer. | Hold the Matt Douglas design review this week; Adam to sort PO coverage. | Adam L (RACV) | This week |
| Inverloch – PV | Delivery | At Risk | One cabin left to panel (Room 310) — recurring rain; a new window may be needed next week. In parallel, comms are being switched on and connected to the local network, with the GMM (metering) board due within ~2 weeks; systems energised progressively as commissioned. Site expected fully energised by end of August. Network / DNSP: SP AusNet — approved. | Secure a dry window for Room 310; install GMM and energise progressively. | David | End Aug |
| Cobram – PV | Delivery | On Track | Fully installed. Roller door on the inverter shed approved and installing in the coming days (PO pending the contractor's onboarding paperwork — Brent to help chase). Shutdown booked 26/08: CES signed and inspector to sign off the battery and MSB upgrade that day, then energise; DNSP approval expected within ~a week (early September). Network / DNSP: Powercore — approved, pending meter amalgamation at shutdown. | Complete roller-door onboarding/PO; energise at the 26/08 shutdown. | David | 26/08 shutdown |
| Cobram – BESS | Delivery | On Track | Trench and transformer works require the HV off, so they complete during the 26/08 shutdown (approx. 2 big days). Fence colours now confirmed by Brent (bushland enclosure / woodland-grey roller door) — fence to be installed before the site is tidied. Actions raised: replace CD's branded hoarding with black mesh wrapping the whole site; assess the tree limb overhanging the battery (Brent to discuss with Andy). Delta commissioning early September. Network / DNSP: Powercore — approval to follow meter amalgamation at shutdown. | Install fence; tidy site (black mesh, rubbish); resolve tree limb; commission (Sept). | David / Brent | 26/08 |
| Cobram – EV | Quoting | On Track | Proposal re-issued to Brett Humphries (copied to Jonathon) on 28/07; one item to finalise, then it is the final version. | RACV to review; David to answer any questions from Brett. | Brett (RACV) | With RACV |
| Noble Park – PV | Delivery | Monitor | Installed and commissioned; CES received. Andrew Nimmo (United Energy) has raised the backstop-testing method — David chasing the email chain (confirming with Vincent first). Half the solar can be energised on one meter once the method is confirmed. | Track down / confirm the backstop-testing method, then energise half. | David | This week |
| Noble Park – BESS | Delivery | Monitor | Installed and commissioned; CES received. CEC accreditation progressing — Delta's test report being finalised this week; CEC approval expected around the 14th, which would close out the grid apps this month. Fence material ordered, install expected next week (penetration to be fire-pillowed and rendered). Rubbish / redundant board inside the switchboard room to be cleared. | Install fence next week; clear site rubbish; close CEC ~14th, then energise. | David | This month |
| Noble Park – EV (Stage 1) | Delivery | Complete | Line marking completed this morning; bays offline today and available for charging from tomorrow. Effectively closed out. | Open for charging tomorrow — close out. | David / Luca | — |
| Noble Park – Retail DC EV | Design | Monitor | Quote tracking to complete next week, then to RACV to review and kick off. Likely an FY28 business case. | Send the quote to RACV once complete (approx. next week). | David | Next week |
| Noble Park – Car Park (Stage 2) | Design | On Track | Quote for the remaining underground chargers (approx. 21 in total) tracking to complete next week, then to RACV to review. | Send the quote to RACV once complete (approx. next week). | David | Next week |
| Cape Schanck – PV | Handover | Complete | Handed over and complete. Booking an O&M reintroduction session with Mark, Brent and Matt Radecki (O&M). | Book the O&M reintroduction session. | David / Mark | — |
| Cape Schanck – BESS | Delivery | On Track | Good progress — core holes drilled, cable trays installed, termite blanket going in today, and a 10-strong crew pulling cables tomorrow, then backfill. Switchboard due late next week, so the ~1-week slip won't extend the finish. Fence approved by the town planner — now pending Carl's sign-off (David to follow up). Delta commissioning 7–11 September. | Pull cables and backfill; install switchboard; get Carl's fence sign-off; commission 7–11 Sept. | David | Sep |
| Goldfields – BESS | Delivery | On Track | Fully commissioned and signed off. Fence approved and material ordered — contractor to prioritise installation as soon as material arrives (expected next week), then energise. | Install the fence on material arrival, then energise. | David | Next week |
| Royal Pines – Stage 1 | Design | On Track | Three-contractor cost breakdown being finalised for Jonathon; SJ Electric (preferred) tightening its price, expected back today/tomorrow. Then to Adam and Jonathon to approve so works can start. | Issue the breakdown to Adam & Jonathon for approval. | David | This week |
| Royal Pines – Stage 2 | On Hold | On Hold | On hold pending completion of Stage 1; to be reworked once Stage 1 is settled. | Progress once Stage 1 is complete. | David | — |
| Royal Pines – BESS | On Hold | On Hold | Design to recommence once Stage 1 is complete. | Recommence design once Stage 1 is complete. | David | — |
| Royal Pines – EV | Design | On Track | RACV endorsement received (Jonathon, 28/07). David to work through the design with Jon. | Progress the Area A design with Jon. | David | In design |
| Healesville – DHW/Boiler | Design | Monitor | Design progressing; most RFIs closed out. Remaining RFIs forwarded to Brent, who is picking up the Grosvenor data request (approx. $4.5k PO, spanning several sites) to close them out — Grosvenor is under-resourced. Amenities modelling (gas instant → heat-pump storage) flagged as an upcoming task. | Brent to close the remaining RFIs via Grosvenor; then finalise design. | David / Brent | This week |

| - Finance & Other Business |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | Detail | Owner | Due | Status |
| As-builts / handover packs | Handover packs (panels, inverters, system sizes, as-builts) being compiled for all sites; Noosa prioritised. Share with Shane (for monitoring/VMS) and Brent for record. Cape Schanck pack already issued — Mark/Shane to forward to Brent. | David | This month | In progress |
| Cobram – heat pump / hot water (emerging) | Hot-water / heat-pump & cooktop replacement enquiry. RFI register being created this week; Stiebel heat-pump unit (newer antifreeze version) confirmed with Sam. Amenities modelling (gas instant → heat-pump storage) to follow. | David / Brent | TBC | Emerging |
| Royal Pines DHW (proposed) | Indicative design cost being sought (Stable) so the load is captured in the max-demand for future upgrades. | David | TBC | Proposed |
| Contracts | Designing before delivery this year. David to send Brent dot-point headlines + latest fee proposals per contractor; Brent to draft contracts for David to sign, ahead of any site works. | David / Brent | Ongoing | Open |

| - Action Register |  |  |  |  |
| --- | --- | --- | --- | --- |
| Item | Detail | Owner | Due | Status |
| Noosa – PV (DNSP) | Energex confirmed; site energising this week (main reception + enclaves live). [Raised 21/07] | Brent C (RACV) | 05/08 | Done |
| Cobram – BESS (fence) | Fence colours confirmed — bushland enclosure / woodland-grey roller door. [Raised 21/07] | Brent C (RACV) | 05/08 | Done |
| Noble Park – EV (Stage 1) | Line marking completed; bays open for charging from tomorrow. [Raised 28/07] | David / Luca | 05/08 | Done |
| Baseline programme | Updated baseline build schedules issued to Brent. [Raised 28/07] | David (CES) | 05/08 | Done |
| Cobram – BESS (tree limb) | Assess the tree limb overhanging the battery — Brent to raise with Andy; David to send Roger's notes / photos. [New 05/08] | Brent C (RACV) | This week | New |
| Noble Park – PV (backstop) | Track down and confirm the backstop-testing method (Andrew Nimmo, United Energy); check with Vincent first, then energise half. [Raised 28/07] | David (CES) | This week | In progress |
| Healesville (RFIs / data) | Brent to close the remaining RFIs via Grosvenor (approx. $4.5k PO across several sites); David to forward the RFI list & PO. [Raised 28/07] | Brent C (RACV) | This week | Carried fwd |
| Royal Pines – S1 (pricing) | Issue the three-contractor cost breakdown to Adam & Jonathon for approval; SJ tightening its price. [Raised 21/07] | David (CES) | This week | In progress |
| Royal Pines – DHW | Get an indicative design cost (Stable) so the load is captured in the max-demand. [Raised 21/07] | David (CES) | TBC | Carried fwd |
| Cobram – heat pump (RFI register) | Create the RFI register for the hot-water / heat-pump replacement and share with Brent. [New 05/08] | David (CES) | This week | New |
| Contracts (admin) | David to send Brent dot-point contractor headlines + fee proposals; Brent to draft contracts. [New 05/08] | David / Brent | Ongoing | New |

Next Meeting

[insert data ¦ Time ¦ Location]